## 프론트엔드
Req_no | 기능 | 화면 예시 | 세부 기능
F_1 | 로그인 페이지
F_2 | 마이페이지 (개인)
F_3 | 회원가입 페이지
F_4 | 상단 메뉴바 (광고 등록, 광고 검색, 로그인, 회원가입 항시 고정)
F_5 | 사이트 관리자 페이지
F_6 | 광고 신청 페이지
F_7 | 광고 조회 페이지
F_8 | 광고 등록 페이지
F_9 | 메인화면
F_10 | 마이페이지 (기업)

## 백엔드
구분 | Req_no | 서비스 (메뉴) | 필요 기능 | 기능 설명 | 비고
공통 | B_1 | 로그인 | 이메일 로그인 | 개인, 기업 자동 구분하여 회원 로그인
|  |  | SNS 로그인 | 카카오톡 회원가입
| B_3 | 회원가입 | 이메일 회원가입 | 이메일로 회원 가입 (개인, 기업 구분)
|  |  | SNS 회원가입 | 카카오톡 회원가입
| B_4 | 상단 메뉴바 | 상단 메뉴바 | 페이지 상단에 지속적으로 메뉴바 노출
| B_9 | 메인화면 | 메인화면 | 사이트 이용법, 정보, 광고등을 노출
개인 | B_2 | 마이페이지 (개인) | 프로필사진 등록/수정 | 프로필 사진 변경
|  |  | 개인정보 수정 | 이름, 이메일, 성별, 차종 정보 수정
|  |  | 계정 비활성화 (선택) | 계정 일시적 비활성화
|  |  | 회원 탈퇴 | 개인 회원 탈퇴
| B_6 | 광고 신청 | 선택한 광고 상세보기 | 선택한 광고 상세정보(가격, 지역, 이미지) 조회
|  |  | 광고 신청 | 차에 부착할 광고 신청
| B_7 | 광고 조회 | 광고 조회 기능 | 신청가능한 기업 최신순 조회
|  |  | 광고 상세조회 기능 | 업종, 가격, 지역별로 신청 가능 기업 조회
기업 | B_10 | 마이페이지 (기업) | 광고 이미지 수정 | 홍보할 기업의 광고 이미지 수정
|  |  | 파트너(개인) 수락 관리 | 광고 희망자 정보 조회 및 수락, 거절기능
|  |  | 업체정보 수정 | 업체 이름, 이메일, 업종 등의 정보 수정
|  |  | 회원 탈퇴 | 기업 회원 탈퇴
| B_8 | 광고등록 | 광고 이미지, 상세정보 등록 | 광고할 지역, 이미지, 차종 등의 정보 등록
관리자 | B_5 | 회원 관리 | 개인회원 관리 | 문제유발 회원 사이트 이용제한 등 회원 관리 기능
기업회원 관리
|  | 사이트 배너 이미지 관리 | 배너 이미지 수정 | 사이트 배너 광고 이미지 수정 기능
|  | 사이트 게시글 관리 | 게시글 관리 | 기업의 광고 이미지, 게시글 제제 등의 CRUD 기능

## WBS
ADD IT WBS (2021.06.28 ~ 2021.07.12)
단계 | 활동 | Task | 수행주체 | 추가 산출물 | 산출물 | 시작일 | 완료일 | 투입일수 | 6월 |  |  | 7월
[9 empty] | 1주 | [6 empty] | 2주
[9 empty] | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2
[9 empty] | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 | 2021-07-02 | 2021-07-03 | 2021-07-04 | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-11 | 2021-07-12
사업관리 | [7 empty] | 7
| 기술분석 | 파트별 기본 프로그래밍 문법 분석 |  |  | 파트별 문법 스터디 자료 | 2021-06-28 | 2021-06-29 | 2 | bar: 2021-06-28 to 2021-06-29
| 기술분석 | 기술 스택 분석 |  |  | 분석 자료 | 2021-06-28 | 2021-06-29 | 2 | bar: 2021-06-28 to 2021-06-29
| 기술분석 | 개발 환경 구성 |  |  |  | 2021-06-29 | 2021-06-29 | 3 | bar: 2021-06-29
프론트 엔드 | [7 empty] | 60
| 메인 페이지 | 메인 페이지 개발 | 김성열 |  | 소스코드 | 2021-07-01 | 2021-07-04 | 4 | bar: 2021-07-01 to 2021-07-04
| 로그인 페이지 | 로그앤 페이지 개발 | 김태호 |  | 소스코드 | 2021-07-01 | 2021-07-04 | 4 | bar: 2021-07-01 to 2021-07-04
| 마이 페이지(개인) - 개인정보수정 | 개인 마이페이지 개발 - 개인정보 수정 화면 개발 | 유태양 |  | 소스코드 | 2021-07-01 | 2021-07-04 | 4 | bar: 2021-07-01 to 2021-07-04
| 마이 페이지(개인) - 광고신청내역 | 개인 마이페이지 - 신청했던 광고내역 조회 화면 개발 | 유태양 |  | 소스코드 | 2021-07-01 | 2021-07-04 | 4 | bar: 2021-07-01 to 2021-07-04
| 마이 페이지(개인) - 광고내역 / 인증 | 개인 마이페이지 - 진행중인 광고신고 및 과제수행(인증) 내역 조회화면 개발 | 유태양 |  | 소스코드 | 2021-07-01 | 2021-07-04 | 4 | bar: 2021-07-01 to 2021-07-04
| 마이 페이지(기업) - 기업정보수정 | 기업 마이페이지 - 기업정보 수정 화면 개발 | 나문오 |  | 소스코드 | 2021-07-01 | 2021-07-04 | 4 | bar: 2021-07-01 to 2021-07-04
| 마이 페이지(기업) - 광고등록내역 | 기업 마이페이지 - 등록한 광고 내역 조회화면 개발 | 나문오 |  | 소스코드 | 2021-07-01 | 2021-07-04 | 4 | bar: 2021-07-01 to 2021-07-04
| 마이 페이지(기업) - 광고내역 / 지급 | 기업 마이페이지 - 광고내역 / 지급내역 조회화면 개발 | 나문오 |  | 소스코드 | 2021-07-01 | 2021-07-04 | 4 | bar: 2021-07-01 to 2021-07-04
| 회원가입 페이지 | 회원가입 페이지 개발 | 김태호 |  | 소스코드 | 2021-07-01 | 2021-07-04 | 4 | bar: 2021-07-01 to 2021-07-04
| 상단 메뉴바 | 상단 메뉴바 (모든 페이지에 노출) | 김성열 |  | 소스코드 | 2021-07-01 | 2021-07-04 | 4 | bar: 2021-07-01 to 2021-07-04
| 광고 신청 페이지 (개인) | 광고 신청 페이지 개발 (광고 상세정보 조회 가능) | 김성열 |  | 소스코드 | 2021-07-01 | 2021-07-04 | 4 | bar: 2021-07-01 to 2021-07-04
| 광고 조회 페이지 | 신청가능 광고 정보 조회 페이지 개발 | 김성열 |  | 소스코드 | 2021-07-01 | 2021-07-04 | 4 | bar: 2021-07-01 to 2021-07-04
| 광고 등록 페이지 (기업) | 광고 등록 페이지 개발 | 김태일 |  | 소스코드 | 2021-07-01 | 2021-07-04 | 4 | bar: 2021-07-01 to 2021-07-04
| 유지보수 | 버그 및 디테일 수정 |  |  | 소스코드 | 2021-07-05 | 2021-07-12 | 8 | bar: 2021-06-28 to 2021-07-12
백엔드
| 이메일 로그인 API | logout, login state check, 개인 / 기업 구분 | 김태호 |  | 소스코드 | 2021-07-05 | 2021-07-08 | bar: 2021-07-05 to 2021-07-08
| SNS 로그인 API | logout, login state check, 개인 / 기업 구분 | 김태호 |  | 소스코드 | 2021-07-05 | 2021-07-08 | bar: 2021-07-05 to 2021-07-08
| 이메일 회원가입(개인) API | 회원가입 (이름, 이메일, 성별, 차종) | 김태호 |  | 소스코드 | 2021-07-05 | 2021-07-08 | bar: 2021-07-05 to 2021-07-08
| 이메일 회원가입(기업) API | 회원가입 (기업명, 업종, …) | 김태호 |  | 소스코드 | 2021-07-05 | 2021-07-08 | bar: 2021-07-05 to 2021-07-08
| SNS 회원가입(개인) API | 회원가입 (이름, 이메일, 성별, 차종) 기능 개발 | 김태호 |  | 소스코드 | 2021-07-05 | 2021-07-08 | bar: 2021-07-05 to 2021-07-08
| SNS 회원가입(기업) API | 회원가입 (기업명, 업종, …) 기능 개발 | 김태호 |  | 소스코드 | 2021-07-05 | 2021-07-08 | bar: 2021-07-05 to 2021-07-08
| 메인화면 API | 메인화면 광고 이미지, 게시글 조회 기능 개발 | 김성열 |  | 소스코드 | 2021-07-05 | 2021-07-08 | bar: 2021-07-05 to 2021-07-08
| 광고 신청(개인) API | 광고 상세 정보 조회, 광고 신청 기능 개발 | 김성열 |  | 소스코드 | 2021-07-05 | 2021-07-08 | bar: 2021-07-05 to 2021-07-08
| 광고 등록(기업) API | 기업의 광고 등록, 게재기능 개발 | 김태일 |  | 소스코드 | 2021-07-05 | 2021-07-08 | bar: 2021-07-05 to 2021-07-08
| 광고 조회 API | 신청가능한 광고 목록 조회 기능 개발 | 김성열 |  | 소스코드 | 2021-07-05 | 2021-07-08 | bar: 2021-07-05 to 2021-07-08
| 마이페이지 (기업) API | 기업계정 정보 CRUD 기능, 등록 광고 관리 기능 개발 | 나문오 |  | 소스코드 | 2021-07-05 | 2021-07-08 | bar: 2021-07-05 to 2021-07-08
| 마이페이지 (개인) API | 개인계정 정보 CRUD 기능, 신청 광고 관리 기능 개발 | 유태양 |  | 소스코드 | 2021-07-05 | 2021-07-08 | bar: 2021-07-05 to 2021-07-08
| 로깅 기능 | 로깅 기능 필요 (클라우드 서버 관리용) | 김태호 |  | 소스코드 | 2021-07-05 | 2021-07-08 | bar: 2021-07-05 to 2021-07-08
| health check api | health check | 김태호 |  | 소스코드 | 2021-07-05 | 2021-07-08 | bar: 2021-07-05 to 2021-07-08
| 추가로 필요한 API |  |  |  | 소스코드 | #N/A | #N/A
| 유지보수 | 버그 및 디테일 수정 |  |  |  | 2021-07-09 | 2021-07-12 | bar: 2021-06-28 to 2021-07-12
클래스 | DTO | DTO 설계 | 공통 |  |  | 2021-07-01 | 2021-07-04 | bar: 2021-07-01 to 2021-07-04
| DAO | DAO 설계 | 공통 |  |  | 2021-07-01 | 2021-07-04 | bar: 2021-07-01 to 2021-07-04
| Service (비즈니스 로직) | Service 설계 | 공통 |  |  | 2021-07-01 | 2021-07-04 | bar: 2021-07-01 to 2021-07-04
| Servlet (컨트롤러) | Servlet 설계 | 공통 |  |  | 2021-07-01 | 2021-07-04 | bar: 2021-07-01 to 2021-07-04
DB | [7 empty] | 6
| 테이블 정의 | 테이블 정의 | 공통 |  |  | 2021-06-28 | 2021-06-29 | 2 | bar: 2021-06-28 to 2021-06-29
| DDL 작성 | DDL 정의 | 공통 |  |  | 2021-06-28 | 2021-06-29 | 2 | bar: 2021-06-28 to 2021-06-29
| CRUD 정의서 | CRUD 정의 | 공통 |  |  | 2021-06-28 | 2021-06-29 | 2 | bar: 2021-06-28 to 2021-06-29
중간보고 | 중간보고 | 미팅 & 진행과정 보고 | 공통 |  |  | 2021-07-02 | 2021-07-02 | 3 | bar: 2021-07-02; 2021-07-08; 2021-07-11
총투입 | [7 empty] | 76 | 5 | 6 | 0 | 17 | 17 | 17 | 17 | 15 | 15 | 15 | 15 | 2 | 2 | 2 | 2

## DB
※ 개발 시 필요 테이블 논의 후 추가
DDL
create table ACCOUNT ( ID VARCHAR2(45) not null primary key, PWD VARCHAR2(50) not null, USER_TYPE NUMBER(1) not null ) / comment on column ACCOUNT.USER_TYPE is '1:개인 2:기업' / create table LOCATION ( LOC_CODE NUMBER(5) not null constraint LOCATION_PK primary key, LOC_NAME VARCHAR2(15) not null ) / comment on column LOCATION.LOC_CODE is '지역코드' / comment on column LOCATION.LOC_NAME is '시군구' / create unique index LOCATION_LOC_CITY_UINDEX on LOCATION (LOC_CITY) / create table COMPANY ( COM_ID VARCHAR2(45) not null constraint COMPANY_PK primary key constraint COMPANY_ACCOUNT_ID_FK references ACCOUNT, COM_NAME VARCHAR2(20) not null, COM_PHONE VARCHAR2(30) not null, COM_EMAIL VARCHAR2(40) not null, COM_ZIPCODE NUMBER(5) not null, COM_ADDR VARCHAR2(255) not null, COM_RM VARCHAR2(10) not null, COM_BT NUMBER not null ) / comment on column COMPANY.COM_PHONE is '전화번호' / comment on column COMPANY.COM_EMAIL is '회사이메일' / comment on column COMPANY.COM_ZIPCODE is '우편번호' / comment on column COMPANY.COM_ADDR is '상세주소' / comment on column COMPANY.COM_RM is '사업자 등록번호' / comment on column COMPANY.COM_BT is '업종코드' /
create table ADVERTISEMENT ( ADV_NO NUMBER not null constraint ADVERTISEMENT_PK primary key, ADV_COM_ID VARCHAR2(45) not null constraint ADV_COMPANY_COM_ID_FK references COMPANY, ADV_LOCATION1 NUMBER not null constraint ADV_LOCATION_LOC_CODE_FK1 references LOCATION, ADV_LOCATION2 NUMBER constraint ADV_LOCATION_LOC_CODE_FK2 references LOCATION, ADV_LOCATION3 NUMBER constraint ADV_LOCATION_LOC_CODE_FK3 references LOCATION, ADV_FEE NUMBER not null, ADV_CARTYPE NUMBER not null, ADV_STARTMONTH DATE not null, ADV_ENDMONTH DATE not null, ADV_DATE DATE default SYSDATE, ADV_TOTAL NUMBER not null ) / comment on column ADVERTISEMENT.ADV_NO is '광고코드' / comment on column ADVERTISEMENT.ADV_CARTYPE is '0 : 차종무관 1 : 경차 2 : 승용차 3 : SUV 4 : 대형' / comment on column ADVERTISEMENT.ADV_DATE is 'default : 현재시각' / comment on column ADVERTISEMENT.ADV_TOTAL is '모집인원' / create unique index COMPANY_COM_EMAIL_UINDEX on COMPANY (COM_EMAIL) / create unique index COMPANY_COM_PHONE_UINDEX on COMPANY (COM_PHONE) / create unique index COMPANY_COM_RM_UINDEX on COMPANY (COM_RM) / create table INDIVIDUAL ( IN_ID VARCHAR2(45) not null constraint INDIVIDUAL_PK primary key constraint INDIVIDUAL_ACCOUNT_ID_FK references ACCOUNT, IN_NAME VARCHAR2(20) not null, IN_PHONE VARCHAR2(30) not null, IN_EMAIL VARCHAR2(40) not null, IN_ZIPCODE NUMBER(5) not null, IN_ADDRESS VARCHAR2(255) not null, IN_BIRTHDAY DATE not null, IN_CAR NUMBER(1) not null ) / comment on column INDIVIDUAL.IN_ZIPCODE is '우편번호' / comment on column INDIVIDUAL.IN_ADDRESS is '상세주소' / comment on column INDIVIDUAL.IN_CAR is '차종 1 : 경차 2 : 승용차 3 : SUV 4 : 대형' / create table APPLY ( APP_NO NUMBER not null constraint APPLY_PK primary key, APP_IN_ID VARCHAR2(45) not null constraint APPLY_INDIVIDUAL_IN_ID_FK references INDIVIDUAL, APP_ADV_NO NUMBER not null constraint APPLY_ADVERTISEMENT_ADV_NO_FK references ADVERTISEMENT, ADD_DATE DATE default SYSDATE not null, APP_STATE NUMBER(1) default 0 not null, APP_BANK VARCHAR2(20) not null, APP_ACNO VARCHAR2(30) not null ) / comment on table APPLY is '광고 지원정보 테이블' / comment on column APPLY.APP_IN_ID is '아이디 (개인)' / comment on column APPLY.APP_ADV_NO is '광고번호' / comment on column APPLY.ADD_DATE is '광고 신청일' / comment on column APPLY.APP_STATE is '신청상태 -1 : 거절 0 : 대기 1 : 수락' / comment on column APPLY.APP_BANK is '입금받을 은행' / comment on column APPLY.APP_ACNO is '계좌번호' / create table PAYMENT ( PAY_NO NUMBER not null constraint PAYMENT_PK primary key, PAY_APP_NO NUMBER not null constraint PAYMENT_APPLY_APP_NO_FK references APPLY, PAY_DATE DATE default SYSDATE not null, PAY_MONTH NUMBER(2) not null, PAY_FEE NUMBER not null ) / comment on column PAYMENT.PAY_APP_NO is '어떤 광고에 대한 지불인지 알기위해' / comment on column PAYMENT.PAY_MONTH is '8월 임금 => 11월에 지급 => 그럼 몇월달 돈을 준건지 알수가 없어 이를 기록하기 위해 만듦' / comment on column PAYMENT.PAY_FEE is '1인당 월 광고지급 금액' / create table VERIFICATION ( VERI_APP_NO NUMBER not null constraint VERIFICATION_APPLY_APP_NO_FK references APPLY, VERI_MONTH DATE not null, VERI_METER NUMBER default 0 not null, VERI_STATE NUMBER(1) default 0 not null, constraint VERIFICATION_PK_2 primary key (VERI_APP_NO, VERI_MONTH) ) / comment on column VERIFICATION.VERI_APP_NO is '신청번호 복합키' / comment on column VERIFICATION.VERI_MONTH is '복합키' / comment on column VERIFICATION.VERI_METER is '인증거리 (GPS 난수입력)' / comment on column VERIFICATION.VERI_STATE is '-1 : 반려(거절) 0 : 대기 1 : 승인' / create unique index INDIVIDUAL_IN_EMAIL_UINDEX on INDIVIDUAL (IN_EMAIL) / create unique index INDIVIDUAL_IN_PHONE_UINDEX on INDIVIDUAL (IN_PHONE) /